## Instructions
Instructions | Enter your team name as specified in the cell below. When doing cross-team and Freshman Seminar acceptance testing, enter the name for the testing group. Fill-in the Test Plan worksheet with all the remaining User Stories in your Product Backlog. As your user stories are refined, add the acceptance criteria for each user story. Use a separate worksheet to provide any specific test case data that the tester needs to use. As tests are performed in each sprint, indicate Pass/Fail. The tester should add initials and a date in the comments column. If the test failed, the tester is required to add additional information about the failure. The status cell will color code based on the test results. The comments cell will color code when a test result exists but no information is entered. Save this test plan with a name formatted as "term-swen-261-sec-letter name", e.g. 2171-swen-261-10-a Speedy Racers.xslx. Submit this file per the instructions specified for the sprint submissions, cross-team testing, and Freshman Seminar testing.
Team Name | Your team name as "term-swen-261-sec-letter name", e.g. 2171-swen-261-10-a Speedy Racers
Testing Team Name | fill in when doing cross-team or Freshman Seminar testing

## Test Plan
User Story | Acceptance Criterion | Sprint 1 | Tester initials; date; comments (required if test failed) | Sprint 2 | Tester initials; date; comments (required if test failed) | Sprint 3 | Tester initials; date; comments (required if test failed)
As a Player I want to sign-in so that I can play a game of checkers. | Given that I have not yet signed in when I see the Home page then I must see a means to sign-in. (such as a link or button) | Pass | RC; 10/10/2018
| Given that I am not signed-in when I do click on the sign-in link then I expect to be taken to the Signin page, with a means to enter a player name. | Pass | RC; 10/10/2018
| Given that no one else is using my name when I enter my name in the sign-in form and click the Sign-in button then I expect system to reserve my name and navigate back to the Home page. | Pass | RC; 10/8/2018
| Given that no one else is using my name when I enter a name with a double quote (`"`) then I expect the system to reject this name and return the sign-in form. (Note: double quote is not a valid character in a Player's name.) | Pass | RC; 10/10/2018
| Given that someone else with my name has signed-in when I enter my name in the sign-in form then I expect the system to reject my sign-in and return the sign-in form. I can then choose a different user name. | Pass | RC; 10/10/2018
| Given that I am signed-in when I navigate to the Home page then I expect to see a list of all other signed-in players. (NOTE: in the next story you will use this list to pick opponents for checkers games.) | Pass | SN; 10/8/2018
| Given that I am not signed-in when I navigate to the Home page then I expect to see a message of how many players are signed-in but not a list of them (for privacy reasons). | Pass | SN; 10/8/2018
As a Player I want to start a game so that I can play checkers with an opponent. | Given that I'm signed in when I view the Home page then I can start a game by selecting a player listed on the Home page. | Pass | WC; 10/14/2018
| Given that the player I selected isn't yet in a game when I select that player then the system will begin a checkers game and assign me as the starting (Red) player and my opponent as the White player. | Pass | WC; 10/14/2018
| Given that the player I selected is already in a game when I select that player then the system will return me to the Home page with an error message. | Pass | WC; 10/15/2018
| Given that I'm waiting for a game when another player selects a game with me then the system will automatically send me to the Game View from the Home page. NOTE: the `home.ftl` HTML includes a `<meta>` tag that tells the browser to refresh the game every 5 seconds; thus you need to update the `GetHomeRoute` controller to handle the situation when a player is assigned a game. | Pass | WC; 10/14/2018
| Given a valid, initial game board when I drag a piece to a white space then the piece should not be droppable. | Pass | WC; 10/15/2018
| Given a valid, initial game board when I drag a piece to an occupied space then the piece should not be droppable. | Pass | WC; 10/15/2018
| Given a valid, initial game board when I drag a piece to an open space then the piece should be droppable. NOTE: In this Story the drop action should not do anything; piece movement will be the focus of future stories. | Pass | WC; 10/14/2018
| Given a valid, initial game board when I view the board in the browser then my pieces are oriented on the bottom of the board grid just like I would see the board if I were playing in the physical world. | Pass | WC; 10/15/2018
As a player I want to move one space diagonally so the game can advance. | Given that I am in a game with a player and it is my turn when I drag one of my pieces to a diagonally adjacent open square then the piece should be moved to that square. |  |  | Pass | SN; 10/30/2018
| Given that I am in a game with a player and it is my turn when I drag one of my pieces to an open square that is not diagonally adjacent, then the move will be reverted because it is invalid. |  |  | Pass | SN; 10/30/2018
| Given is is my turn in a game with a player and it is my turn when I make a valid simple move, then all of my pieces except the one I moved will not be moveable. |  |  | Pass | SN; 10/30/2018
As a player I want to submit my turn so my opponent can take their turn. | Given I have selected at least one valid move when I click the Submit Turn button then the move will be submitted and it will be my opponent's turn. |  |  | Pass | RC; 11/3/2018
| Given I have selected at least one valid move when I click the Submit Turn button then none of my pieces will be moveable. |  |  | Pass | RC; 11/3/2018
| Given a turn has been submitted **when** the page refreshes then the board will be updated with the new move. |  |  | Pass | RC; 11/3/2018
| Given that it is not my turn when I click submit turn it does not do anything. |  |  | Pass | RC; 11/3/2018
As a player I want to jump over an opponent's piece so that I take their piece away. | Given that it is my turn when I move a piece that jumps an opponent piece then the move is accepted as valid. |  |  | Pass | RC; 10/30/2018
| Given I have selected a single jump move when I submit my turn then the opponent's piece that was jumped is removed from the board. |  |  | Pass | RC; 10/30/2018
| Given I can make a single jump move when I attempt to make a simple move then the move is rejected as invalid. |  |  | Pass | RC; 10/30/2018
| Given that it is my turn when I move piece that tries to jump my own piece, then it is invalid |  |  | Pass | RC; 10/30/2018
As a player I want to be notified when it is my turn so I can take my turn. | Given my opponent has completed their turn when I check to see if it is my turn then I will be notified that it is my turn |  |  | Pass | SN; 11/3/2018
| Given that it is my turn when I am still deciding on moves then the game does not update |  |  | Pass | SN; 10/31/2018
As a player I want to jump multiple of my opponents pieces so that I capture all of them.
As a Player, when I can jump different pieces, I want to be able to choose which piece to jump, so that I can make the best move.
As a player I want to undo my last selected move so I can edit my selected move if I don't like it.
As a player I want to make my pieces king pieces so that I can move them forward and backwards.
As a player I want to win the game if my opponent does not have pieces or cannot make a move so that I can feel good about myself.
As a player I want to forfeit a game I am playing so that I don't have to keep playing.
As a player I want to win the game when my opponent forfeits so that I can brag about to my friends.
As a player, I want to the game to prevent me from an illegal move so that I follow the rules of American 🇺🇸 Checkers.
As a player I want to know who's turn it is so that I know when it is my turn to make a move
As a player, when I am done playing, I want to log out so that I can stop playing checkers
As a player I want to be asked to confirm my resignation so I don't accidentally resign from a game.
As a Player, I want to automatically resign from my current game when I sign out, so that it does not appear that I am still playing after I sign out.
As a player, I want to see the names of the people I'm playing against so I can keep track of my games.
As a player I want to join a game while playing another so that I don't have to wait around for my opponent as much.
As a player I want to select my current game so that play the right game.
As a player, I want to be notified when it is my turn in one of my games so that I know when I need to make a move.
As a player I want to create an asynchronous game so that I can play a game against someone who may not be logged in.
As a Player I want to be told what move my opponent made so that I can be updated on how the game changed.